IAC 2026 — Team Plan

Submit before 14 September 2026

Where we are now: The simulation is finished and tested. It already gives us our main result — the gate cuts unnecessary route changes by about 65% and saves rerouting energy, while barely affecting delay. The building is done. What's left is making it stronger, writing it up, and showing it off.

First job for everyone: read the code guide (README) until you can explain the basic idea. Nobody works on a part they don't understand.

# The four jobs

Four kinds of work happen at the same time. Each person owns one lane. Some lanes are busier in some weeks — that's normal.

- Research: find papers, citations, and the formulas we still need. Busiest early.

- Technical: turn ideas into simulation code. The big one this round: build the auto-threshold. Busiest weeks 2–5.

- Visuals: build the two-screen view — real satellites on one side, the twin's delayed picture on the other. Busiest weeks 3–7.

- Writing: write the paper, starting as soon as we have results. Busiest weeks 4–8.

# The week-by-week plan

| Wk | Technical | Research | Visuals | Writing |
| --- | --- | --- | --- | --- |
| 1 | Team meeting: decide who does what, and decide what 'optimize the threshold' means for us. Everyone reads the code guide first. | Start collecting papers, citations, and the math formulas we still need. | Planning only, no code yet. | Nobody yet. |
| 2 | Build the second result graph: how the twin's errors grow as the data delay grows. | Keep gathering sources. Draft the 'what others did before us' section. | Sketch the two-screen idea on paper. | A writer sets up the empty document and section headings. |
| 3 | Start the auto-threshold: the gate sets its own strictness based on how busy the network is. | Lock down citations. Double-check the energy-cost source. | Build screen 1: the real satellites and traffic. | Start writing the setup and methods sections. |
| 4 | Finish and test the auto-threshold. Run all final simulations. FREEZE the code after this week. | Hand finished sources to the writers. | Build screen 2: the twin, with its delayed, wrong picture. | Keep writing methods from the code guide. |
| 5 | Make all final graphs, clean and clear. Team checks: do the results hold up? | Help writers with any missing references. | Connect the two screens so the gap between them is visible. | Full first draft: intro, method, results, conclusion. |
| 6 | Re-run anything that needs a cleaner number. | Proofread all references. | Polish the visuals for the live presentation. | Fix the draft after everyone reads it. Match every claim to a graph. |
| 7 | Final check: every number is sourced or swept. Nothing invented. | Final reference check. | Rehearse the demo until it runs smoothly. | Abstract and IAC formatting. |
| 8 | Submit early. Do NOT save real work for this week. | Done. | Prepare what to say during the interactive session. | Final read. SUBMIT before Sept 14. |

# How to explore the demo (for the warm-up before meeting 1)

Open config.py. Change ONE of these, save, run simulate.py, and watch how delay / switches / energy move:

- GATE_THRESHOLD — the strictness knob. Try 0.95, 0.80, 0.60.

- TELEMETRY_DELAY_S — how stale the twin is. Try 0, 10, 20.

- BACKGROUND_LOAD_MEAN — how busy the network is. Try 0.3, 0.6.

Change one thing at a time. Come to the meeting able to answer: what happens to switches and delay when you tighten the gate? What happens when the twin gets staler?

Don't panic if: delay=0 makes the gate look useless (that's correct — a perfect twin needs no gate), or a tiny constellation breaks (the geometry can't exist below ~18 sats per plane). Don't touch anything marked [PHYSICS].

# Three rules that keep us out of trouble

We already made a version that fell apart. It fell apart for these exact reasons:

- Every number needs a source. Physics, or a real paper, or calculated, or a tested range. Never made up.

- No new features after week 4. After that, only graphs and writing.

- One person owns the code. Everyone else proposes changes to them and they approve. Do not all edit the same files.

# The decision for meeting 1

Agree the paper's main point. Three choices, safest to riskiest:

- A — Show the tradeoff. "Here's the strictness knob, here's what each setting costs." Already done. Safe. A full paper alone.

- B — Auto-tune the knob. The gate sets its own strictness. Builds on A. This is what we aim for.

- C — New routing to beat everyone on delay. Big and risky, basically a second paper. Mention as future work; don't build now.

Suggestion: lock in A, aim for B, mention C. Then we can't lose — even if B runs out of time, A is a complete paper.